# Project Payment Planner MVP Timeline

Proposed delivery roadmap | 15 October 2026

Build a usable pilot MVP in approximately 6 to 8 weeks, assuming one developer working consistently. The first release will help an owner create a project, enter expenses and expected receipts, identify a cash shortage, adjust the payment schedule and export a plan for client discussion.

Timing is indicative. Sprint dates, ownership and budget remain to be agreed. Weeks below are relative to the project start; longer ranges allow for calculation and scenario work.

# Delivery timeline

| Sprint | Indicative timing | Outcome |
| --- | --- | --- |
| 0 | Week 1 | Validated audience and agreed scope |
| 1 | Week 2 | Sign-in and saved project setup |
| 2 | Week 3 | Expenses and payment milestones |
| 3 | Week 4 or Weeks 4 to 5 | Cash forecast and gap detection |
| 4 | Next 1 to 2 weeks | Scenarios, versions and printable export |
| 5 | Final week | User pilot and release readiness |

# First release scope

Include one currency per project; manual project, expense, deposit and milestone entry; expected receipt dates including payment terms; a running cash balance and funding gap; explainable adjustments; delayed-receipt and increased-expense scenarios; saved projects and schedule versions; browser print to PDF.

Defer bank connections, payment processing, automated reminders, AI explanations, client portals, industry templates, actual-payment tracking and combined forecasts across projects.

# Sprint steps and completion criteria

## Sprint 0 Validate and define

Duration: 1 week. Interview 5 to 8 prospective users and review their current spreadsheets or tools. Choose one initial segment and country, agree on scope, and collect realistic project examples.

Complete when: A clear target user, a repeated problem and 3 to 5 reference projects.

## Sprint 1 Foundation and project setup

Duration: 1 week. Set up React, TypeScript, Vite and Tailwind. Configure Supabase and a Cloudflare preview deployment. Implement sign-in, record ownership, and project creation and editing.

Complete when: A user can sign in, save and reopen a project, and access only their own records.

## Sprint 2 Expenses and payment milestones

Duration: 1 week. Build expense entry and deposit and milestone forms. Capture payment terms and expected receipt dates. Validate required fields and payment totals. Store money in integer cents.

Complete when: A complete project schedule can be entered, with errors clearly explained.

## Sprint 3 Cash forecast and gap detection

Duration: 1 to 2 weeks. Build and test the calculation engine. Show a cash timeline and running balance. Highlight the first shortage and maximum funding gap, and explain assumptions.

Complete when: Results match independently checked examples, including the project plan example with a $1,000 gap.

## Sprint 4 Adjustments scenarios and export

Duration: 1 to 2 weeks. Allow deposit and milestone adjustments and explain their effect. Add receipt-delay and expense-increase scenarios. Preserve schedule versions and build a printable plan.

Complete when: A user can compare a revision with the original schedule and export a readable version.

## Sprint 5 Pilot and release readiness

Duration: 1 week. Observe 3 to 5 users completing the journey. Fix calculation and usability issues. Verify record isolation, mobile layouts, exports, service quotas and deployment configuration.

Complete when: Users complete the journey independently, with no known critical calculation or access issues.

# Decisions before development

Initial audience: use Australian freelancers and small agencies delivering fixed-price projects as the starting hypothesis; confirm it during validation.

Cash definition: treat starting cash as money available to allocate to this project.

Tax convention: agree on consistent GST-inclusive or GST-exclusive inputs.

Same-day transactions: decide how receipts and expenses on the same date affect the forecast.

Date rules: distinguish milestone completion, invoice timing and expected receipt.

Version rules: define when saving changes creates a new schedule version.

# Calculation and suggestion rules

Keep forecast receipts separate from confirmed payments. Use expected receipt dates rather than assuming payment on milestone completion. Enforce ownership in database access policies independently of the interface.

Start with simple, explainable suggestions. For example, an additional $1,000 received before an expense could close a $1,000 gap. Respect configured deposit constraints and show any remaining shortage when a feasible schedule cannot be found.

# Immediate next steps

Write a one-page MVP scope with explicit exclusions.

Prepare a short interview guide and recruit prospective users.

Create reference projects covering no gap, a deposit shortfall and a late payment.

Sketch the journey: Projects > Setup > Expenses > Milestones > Forecast > Export.

Turn Sprint 1 into development tickets with clear acceptance criteria.

# Pilot success measures

The key release test is whether an owner can discover a funding gap and produce a better payment schedule without help. Measure time to produce a plan, workflow completion, understanding of the gap, and whether the owner changes proposed client payment terms. Set numerical targets after initial research.

Source: project_payment_planner_project_plan_v2.pdf, dated 15 October 2026. This timeline expands the proposed delivery stages into actionable sprints.